## Actions & Commitments
Last Update: | 2022-02-14
Update Time: | 5:00PM
Updater: | David | [7 empty] | Add any timely updates or comments along this timeline for long opened actions
Priority | Owner | Task | For Deliverable | Category | Status | Opened | Due | Closed | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-12 | 2018-10-13 | 2018-10-14 | 2018-10-15 | 2018-10-16 | 2018-10-19 | 2018-10-20 | 2018-10-21 | 2018-10-22 | 2018-10-23 | 2018-10-26 | 2018-10-27 | 2018-10-28 | 2018-10-29 | 2018-10-30 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-16 | 2018-11-17 | 2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-30 | 2018-12-01 | 2018-12-02 | 2018-12-03 | 2018-12-04 | 2018-12-07 | 2018-12-08 | 2018-12-09 | 2018-12-10 | 2018-12-11 | 2018-12-14 | 2018-12-15 | 2018-12-16 | 2018-12-17 | 2018-12-18 | 2018-12-21 | 2018-12-22 | 2018-12-23 | 2018-12-24 | 2018-12-25 | 2018-12-28 | 2018-12-29 | 2018-12-30 | 2018-12-31 | 2019-01-01 | 2019-01-04 | 2019-01-05 | 2019-01-06 | 2019-01-07 | 2019-01-08 | 2019-01-11 | 2019-01-12 | 2019-01-13 | 2019-01-14 | 2019-01-15 | 2019-01-18 | 2019-01-19 | 2019-01-20 | 2019-01-21 | 2019-01-22 | 2019-01-25 | 2019-01-26 | 2019-01-27 | 2019-01-28 | 2019-01-29 | 2019-02-01 | 2019-02-02 | 2019-02-03 | 2019-02-04 | 2019-02-05 | 2019-02-08 | 2019-02-09 | 2019-02-10 | 2019-02-11 | 2019-02-12 | 2019-02-15 | 2019-02-16 | 2019-02-17 | 2019-02-18 | 2019-02-19 | 2019-02-22 | 2019-02-23 | 2019-02-24 | 2019-02-25 | 2019-02-26
| Cameron | Add additional user stories to product backlog. | Backlog | 50-PROJ MGMT | 2-CLOSED | 2021-10-01 | 2021-10-06 | 2021-10-06
| Kyle | Define scope for user stories for Release I | Backlog | 50-PROJ MGMT | 2-CLOSED | 2021-10-01 | 2021-10-06 | 2021-10-06
| David | Complete and send meeting minutes in 2 business days | Meeting minute | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2021-10-01 | 2021-10-06 | 2021-10-06
| Serge | Send commit email explaining the scope for Release I. Also, give detail what the deliverables will be. |  | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2021-10-01 | 2021-10-15 | 2021-10-15
| Cameron | Decompose User Story (D1) | Backlog | 50-PROJ MGMT | 2-CLOSED | 2021-10-15 | 2021-10-15 | 2021-10-15
| Team | Restructure Product Backlog | Backlog | 50-PROJ MGMT | 2-CLOSED | 2021-10-15 | 2021-10-20 | 2021-10-20
| Kyle | Speak with other Dev Project team about use of Compiler/Interpreter and language priority | Project design | 02-ARCH | 2-CLOSED | 2021-10-15 | 2021-10-15 | 2021-10-15
| Serge | Send Commitment Email for Sprint 1 |  | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2021-10-15 | 2021-10-20 | 2021-10-20
| Kyle | Map new decisions to backlog | Backlog | 50-PROJ MGMT | 2-CLOSED | 2021-12-03 | 2021-12-08 | 2021-12-08
| Cameron | Update changes to backlog for sprint 2 | Backlog | 50-PROJ MGMT | 2-CLOSED | 2021-12-03 | 2021-12-08 | 2021-12-08
| Serge | Send link for backlog to Allan | Client support | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2021-12-03 | 2021-12-08 | 2021-12-08
| Kyle | Email Allan about Clara Courses Winter 2022 |  | 51-ISSUES\RISKS | 2-CLOSED | 2022-01-26 | 2022-01-31 | 2022-01-26
| Serge | Update Action Item Register |  | 50-PROJ MGMT | 2-CLOSED | 2022-01-26 | 2022-01-31 | 2022-01-27
| David | Update Lessons Learnt tab |  | 50-PROJ MGMT | 2-CLOSED | 2022-01-26 | 2022-01-31 | 2022-01-26
| Cameron | Complete Meeting Minutes |  | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2022-01-26 | 2022-01-31 | 2022-01-26
| Serge | Complete Process Memo |  | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2022-01-31 | 2022-01-31 | 2022-01-31
| David | Commit Email |  | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2022-01-31 | 2022-01-31 | 2022-01-31
| Kyle | Add Best Practices tasks in Azure |  | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2022-01-31 | 2022-01-31 | 2022-01-31
| Santiago | Complete Meeting Minutes |  | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2022-01-31 | 2022-01-31 | 2022-01-31
| Francis | Complete Meeting Minutes |  | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2022-02-09 | 2022-02-09
| Kyle | Deploy to cstest |  | 20-DOCUMENTATION/TRAINING | 1-OPEN | 2022-02-09 | 2022-02-09
| David | Email Meeting Minutes + cstest link |  | 20-DOCUMENTATION/TRAINING | 1-OPEN | 2022-02-09 | 2022-02-09
| David | Update Action Item Register |  | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2022-02-14 | 2022-02-14 | 2022-02-14
| Serge | Update Lessons Learnt tab |  | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2022-02-14 | 2022-02-14 | 2022-02-14
| Francis | Complete Meeting Minutes |  | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2022-02-14 | 2022-02-14 | 2022-02-14
| Santiago | Complete Meeting Minutes |  | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2022-02-14 | 2022-02-14 | 2022-02-14
| Shuai | Send Meeting Minutes |  | 20-DOCUMENTATION/TRAINING | 2-CLOSED | 2022-02-14 | 2022-02-14 | 2022-02-14
Note on B1: richard: Update this every time the spreadsheet is updated so we know last modification times stamp

## Retrospective
Last Update: | 2021-12-03
Update Time: | 14:00
Updater: | Francis
Retrospective, Sprint # | Date Added | Scribe | Team member | Went Well | Not Well | Lessons Learnt | What bugs us/mysterious?
1 | 2021-10-07 | Serge | Kyle | Dry-run went well with good feedback from Richard | Presentation speakers not well split. Moc not well split either, could have used more input from all team members | Review individually then discuss in meeting | Database modeling
1 | 2021-10-07 | Serge | Cameron | Overall work well split | Presentation could have been better spaced. Could have elaborated more on certain points | Power point order- make sure to start by more important (prioritize) | Knows everything
| 2021-10-07 | Serge | Shuai | Good architecture | Difficulty interacting with team | Use more than one scribe | Sending emails from browser
| 2021-10-07 | Serge | David | Presentation went well | Slow start | Ask more questions | Online compiler
| 2021-10-07 | Serge | Francis | Class time well spent | Sometime we all focus on one thing | Not all look at same monitor | Online compiler
| 2021-10-07 | Serge | Santiago | Good chemistry in group | Sometime we all focus on one thing | Not all look at same monitor | Online compiler
| 2021-10-07 | Serge | Serge | Got a lot of details out of Owner(Allan) | Disorganized at beginning | Need to prepare ahead of meeting and class work time | Online compiler, Clara
2 | 2021-12-03 | Francis | Kyle | Setting up Clara. Dry-run went well. | Workflow, database cascading issues and identity issues. | Look back to re-use code. Don't commit code a day before.Dry run with the correct version. | Uploading code for student side.
| 2021-12-03 | Francis | Cameron | Good job completing tasks. Did better than other team. | Avoid last minute pushes before sprint review. | Borrow code from others. | None
| 2021-12-03 | Francis | Shuai | Successful error handling. | User requirements. | Right way to use git and branches. | None
| 2021-12-03 | Francis | David | Setting up Clara. Dry-run went well. | Workflow for teacher. Insufficient planning for workflow. | Have someone test before deployment. Make sure to do pending review. | Submitting to API.
| 2021-12-03 | Francis | Francis | Practices for presentation helped. | Tasks were not clear, not tasked out correctly. | Do testing with deployment version. | None
| 2021-12-03 | Francis | Santiago | Setting up the back-end went well. Dry-run really helped. Sprint review got good feedback. | Agrees with David. Workflow didn’t go well. | Doing a dry-run before. More collaboration with the team. | None
| 2021-12-03 | Francis | Serge | Got everything done. | Better job at coordinating structure. | More testing. Need to be more aware of messages and changes from the team. | Figure out flow + sending code as a student.
Note on B1: richard: Update this every time the spreadsheet is updated so we know last modification times stamp

## Lessons Learnt (Team)
Last Update: | 2018-09-28
Update Time: | 14:00
Updater: | Richard
Lesson # | Date Added | By | Lessons Learnt
1 | 2018-09-28 | Richard | (Sample) How to use the Lessons learnt tab in this spreadsheet
2 | 2022-01-26 | Kyle | Review individually then discuss in meeting
| 2022-01-26 | Cameron | Power point order- make sure to start by more important (prioritize)
| 2022-01-26 | Shuai | Use more than one scribe
| 2022-01-26 | Francis | Not all look at same monitor
| 2022-01-26 | Serge | Need to prepare ahead of meeting and class work time
| 2022-01-26 | Kyle | Don't commit code a day before.
| 2022-01-26 | Cameron | Borrow code from others.
| 2022-01-26 | Shuai | Right way to use git and branches.
| 2022-01-26 | David | Make sure to do pending review.
| 2022-01-26 | Francis | Do testing with deployment version.
| 2022-01-26 | Santiago | Doing a dry-run before. More collaboration with the team.
| 2022-01-26 | Serge | More testing. Need to be more aware of messages and changes from the team.
Note on B1: richard: Update this every time the spreadsheet is updated so we know last modification times stamp
Note on B6: richard: Update this every time the spreadsheet is updated so we know last modification times stamp

## ATTENDANCE
 | time axis 2018-09-28 to 2019-02-26
Meeting Description | bar: 2018-09-28 to 2018-11-20
Scrum | 2018-09-28: MemberA, MemberB, MemberC, …
Ragnar Paulson | 2018-09-28: OoO; 2018-09-29: x; 2018-09-30: x; 2018-10-02: N/A; 2018-10-06: N/A; 2018-10-08: N/A; 2018-10-13: N/A; 2018-10-15: N/A; 2018-10-19: N/A; 2018-10-20: N/A; 2018-10-22: N/A

## PARAMETERS
STATES
0-NEW
1-OPEN
2-CLOSED
3-BLOCKED
VARIOUS
INFO
MONITOR
TEAM
Kyle
Cameron
Shuai
David
Francis
Santiago
Serge
TOPIC
01-REQ
02-ARCH
03-DEVELOPMENT
05-TESTING
07-SCRIPTS/UTILITIES
11-DEFECTS
12-HANDOVER
14-PROD READINESS
19-ACCEPTANCE
20-DOCUMENTATION/TRAINING
50-PROJ MGMT
51-ISSUES\RISKS
90-ENVIRONMENT
99-MISC